## Gantt Chart
WeCasa | [5 empty] | Gantt Chart Template © 2020 by Vertex42.com
|  |  |  | Project Start: | 2022-08-29
|  |  |  | Display Week: | 1 | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01
 | time axis 2022-08-29 to 2023-05-07
[6 empty] | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S | M | S | S | S | S | S | S
PERSON | PROGRESS |  | START | DAYS | END | 2022-08-30: TIME FRAME
Joshua | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Githel | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Matthew | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Judy | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Haley | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Allison | 100% |  | 2022-08-29 | 9 | 2022-09-07 | 2022-08-29: Project Proposal
Sprint 1 |  | - | 2022-09-07 | 7 | 2022-09-14
Joshua | 100% |  | 2022-09-07 | 26 | 2022-10-03 | 2022-09-07: Project Proposal Revision
Joshua | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Schematic
Joshua | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Document
Githel | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: BRD
Githel | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Plan
Githel | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Roadmap
Githel | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Document
Githel | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Schematic
Matthew | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Plan
Matthew | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: BRD
Judy | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Plan
Judy | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: BRD
Haley | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Plan
Haley | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Schematic
Haley | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Document
Allison | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Gantt Chart
Allison | 100% |  | 2022-09-07 | 26 | 2022-10-03 | 2022-09-07: Project Proposal Revision
Allison | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: Project Plan
Allison | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Schematic
Allison | 100% |  | 2022-09-27 | 7 | 2022-10-04 | 2022-09-27: HLD Document
Milestone 1 Due |  | -
Team Review 1 |  | -
Sprint 2 |  | - | 2022-10-06 | 12 | 2022-10-18
Joshua | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Joshua | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Githel | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Githel | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Matthew | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Matthew | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Judy | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Judy | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Haley | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Haley | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Allison | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Network Diagram
Allison | 0% |  | 2022-10-06 | 12 | 2022-10-18 | 2022-10-06: Low Level Design
Sprint 3 |  | - | 2022-10-20 | 10 | 2022-10-30
Joshua | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Registration
Githel | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Registration
Matthew | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Registration
Judy | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Login
Haley | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Login
Allison | 0% |  | 2022-10-20 | 10 | 2022-10-30 | 2022-10-20: Login
Sprint 4 |  | - | 2022-11-01 | 7 | 2022-11-08
Joshua | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logout
Githel | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logging
Matthew | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logout
Judy | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logout
Haley | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logging
Allison | 0% |  | 2022-11-01 | 7 | 2022-11-08 | 2022-11-01: Logging
Milestone 2 Due |  | -
Team Review 2 |  | -
Sprint 5 |  | - | 2022-11-10 | 12 | 2022-11-22
Joshua | 0% |  | 2022-11-10 | 12 | 2022-11-22 | 2022-11-10: Creating Groups
Matthew | 0% |  | 2022-11-10 | 12 | 2022-11-22 | 2022-11-10: Deleting Groups
Githel | 0% |  | 2022-11-10 | 12 | 2022-11-22 | 2022-11-10: Authorization
Haley | 0% |  | 2022-11-10 | 12 | 2022-11-22 | 2022-11-10: Permissions
Githel | 0% |  | 2022-11-15 | 10 | 2022-11-25 | 2022-11-15: Adding Members
Judy | 0% |  | 2022-11-15 | 10 | 2022-11-25 | 2022-11-15: Removing Members
Allison | 0% |  | 2022-11-10 | 12 | 2022-11-22 | 2022-11-10: Authorization
Sprint 6 |  | - | 2022-11-24 | 12 | 2022-12-06
Judy | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Deletion
Judy | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Bill of Materials
Josh | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Deletion
Joshua | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Bill of Materials
Githel | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Recovery
Githel | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Bill of Materials
Haley | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Recovery
Haley | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Bill of Materials
Matthew | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Deletion
Allison | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Bill of Materials
Allison | 0% |  | 2022-11-24 | 12 | 2022-12-06 | 2022-11-24: Account Recovery
Milestone 3 Due |  | -
Team Review 3 |  | -
|  | - | 2022-12-14 |  | 2023-01-29 | 2022-12-17: WINTER BREAK
SEMESTER 2
Sprint 7 |  | - | 2023-02-02 | 12 | 2023-02-14
Joshua | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Updating Profile
Haley | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Updating Profile
Githel | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Updating Profile
Matthew | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Budget Sharing Bar
Judy | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Budget Sharing Bar
Allison | 0% |  | 2023-02-02 | 12 | 2023-02-14 | 2023-02-02: Budget Sharing Bar
Sprint 8 |  | - | 2023-02-16 | 12 | 2023-02-28
Joshua | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: App Settings
Githel | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: Customizing Groups
Joshua | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: App Settings
Judy | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: Bulletin Board
Matthew | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: Bulletin Board
Haley | 0% |  | 2023-02-16 | 12 | 2023-02-28 | 2023-02-16: Customizing Groups
Sprint 9 |  | - | 2023-03-02 | 12 | 2023-03-14
Haley | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Chore List
Haley | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Grocery List
Judy | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Uploading a file
Judy | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Grocery List
Matthew | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Removing a file
Matthew | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Uploading a file
Githel | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Chore List
Githel | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Grocery List
Allison | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Uploading a file
Allison | 0% |  | 2023-03-02 | 12 | 2023-03-14 | 2023-03-02: Removing a file
Sprint 10 |  | - | 2023-03-16 | 8 | 2023-03-24
Joshua | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: User Feedback
Haley | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: Incomplete Task Summary
Judy | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: Round Tracking Bar
Githel | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: Incomplete Task Summary
Matthew | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: Round Tracking Bar
Allison | 0% |  | 2023-03-16 | 8 | 2023-03-24 | 2023-03-16: User Feedback
|  | - | 2023-03-25 | 9 | 2023-04-03 | 2022-12-17: WINTER BREAK; 2023-03-25: SPRING BREAK
Sprint 11 |  | - | 2023-04-06 | 12 | 2023-04-18
Joshua | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Reminders
Haley | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Reminders
Matthew | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Nudging
Githel | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Calendar
Judy | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Calendar
Allison | 0% |  | 2023-04-06 | 12 | 2023-04-18 | 2023-04-06: Nudging
Sprint 12 |  | - | 2023-04-20 | 14 | 2023-05-04
Joshua | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2023-04-20: Analytics Dashboard
Haley | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2022-09-02: fappf; 2023-04-20: Analytics Dashboard
Joshua | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2023-04-20: Unit Testing
Githel | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2023-04-20: Unit Testing
Joshua | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2023-04-20: Unit Testing
Allison | 0% |  | 2023-04-20 | 14 | 2023-05-04 | 2023-04-20: Unit Testing
Formulas:
END = [START]+[DAYS]
START = MIN([START, row below]:D48)

## Help
Help
Instead of detailed help worksheet, please do the following if you have questions about how this spreadsheet works, or how to use this spreadsheet.
1) Watch the Video Tutorial on YouTube
https://youtu.be/8eKk0M2zGIk
2) Read the Following Page
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Although the content on the above page was created originally for the Excel template, most of the information about the use of formulas and ways to customize the Gantt chart apply just as well to the Google Sheets version.
Formula for % Complete of a summary task, based on its sub tasks:
SUMPRODUCT(days_range,percent_complete_range)/SUM(days_range)
To show the % Complete within the bars in the Gantt chart:
Select a cell within the Gantt chart area and go to Format > Conditional Formatting, then "turn on" the grey bar rule by changing 1=0 to 1=1 within the AND function.

## TermsOfUse
Simple Gantt Chart for Google Sheets
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2020 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## GanttChartPro
Gantt Chart Template Pro for Google Sheets
Gantt Chart Template Pro, by Vertex42.com, is a spreadsheet template designed originally for Microsoft Excel that offers more features than the free version. When you purchase it, you will also get a link to download the Pro version for Google Sheets!!
Learn More About Gantt Chart Template Pro
- Visit the web page above to view screenshots and watch demo videos
Features in the Pro version for Google Sheets
Define task durations by specifying the number of Work Days
- In this free version, the inputs to define a task are the Start Date and the Calendar Day duration. In the Pro version, the default option is to enter the Start Date and the number of Work Days.
Choose whether to define task durations using Calendar Days or Work Days or End Dates
- The Pro version includes a larger set of template rows that provide more options for defining the Start date, End date, duration, and dependency of tasks.
Exclude holidays from work days
- List holidays and other non-working days in a separate sheet. When defining task durations using Work Days, these dates will be excluded.
Define what you mean by "Weekend" when using Work Days
- The Pro version allows you to define exactly which day(s) of the week you want to use as your weekend. The default is Saturday and Sunday.
Color-Code bars in the Gantt chart
- The Pro version includes a column for entering a color code like "k", "r", or "y" to change the color of the bars in the Gantt chart. The Help worksheet explains some advanced formulas that you could use in the Color column to automatically color a bar based on the name in the Lead column.
Define tasks dependences by specifying the predecessor WBS
- The template rows include an option for entering a Predecessor WBS. The Start date will be calculated as the day following the End date of the predecessor.